# Technical Flow Document: UNICEF Web Analytics Tender

Scope: D1.1, D1.2, D2, A1-A5 and PM (TOR Section III). Diagrams are supplied as Mermaid source; paste into mermaid.live, GitHub, Notion or VS Code to render. Statements marked (assumption) come from section 14.4.

# 1. Scope to be priced and delivered

| Ref | Scope item | Type | Key facts from the tender |
| --- | --- | --- | --- |
| D1.1 | Server-side GTM: evaluation and recommendation | One-off | Measured unicef.org data, Azure design with UNICEF DID, data-protection assessment, written go/no-go presented to stakeholders |
| D1.2 | Server-side GTM: implementation and migration | One-off (only if go) | Tagging server, first-party subdomain, tag migration, server-side consent, parallel run, cutover and rollback, handover |
| D2 | Unified data warehouse with AI analytics layer | One-off | Cloudflare logs, GA4 in BigQuery, social analytics in one data model; plain-language querying; automated reporting and anomaly detection |
| A1 | GTM and tracking infrastructure | Monthly | Container review, change requests with stage testing, pixels, Meta CAPI, consent mode, cross-domain guidance |
| A2 | Google Analytics 4 | Monthly | Governance of 180+ properties, new property requests, Google Ads links, BigQuery datasets, data-quality monitoring |
| A3 | Search Console and SEO/GEO tooling | Monthly | 176 sites, access governance, sitemaps, error routing, SEO platform setup, AI-search visibility across Google AI Overviews, ChatGPT, Gemini, Perplexity, Copilot |
| A4 | Dashboards and reporting | Monthly | Looker Studio for 150+ offices, cross-channel SEO, GEO and campaign reporting |
| A5 | Capacity building and training | Monthly | Up to 5 hours per quarter, recordable, materials shared; ad hoc advisory; trend research |
| PM | Project management | Monthly | Dedicated; single point of contact; project plans, regular reports, budget control |

The tender prices the three one-off deliverables as separate line items, so each needs its own task-level estimate in Annex C1 bis.

# 2. Delivery workflow (phasing and gates)

flowchart TD

K[Kick-off: access model, named users, federated identity] --> PM[PM: plans, reports, budget control]

K --> RUN[Run services: A1 GTM, A2 GA4, A3 GSC/SEO/GEO, A4 Dashboards, A5 Training]

K --> D11[D1.1 Server-side GTM evaluation, months 2-5]

D11 --> M1[Measure unicef.org data]

M1 --> M2[Azure design with UNICEF DID]

M2 --> M3[Data-protection assessment]

M3 --> REC[Written go/no-go to stakeholders]

REC -->|No-go| STOP[Document findings, stay client-side under A1]

REC -->|Documented UNICEF go| D12[D1.2 Implementation and migration]

D12 --> S1[Tagging server on UNICEF-funded Azure]

S1 --> S2[First-party subdomain]

S2 --> S3[Tag migration and server-side consent]

S3 --> S4[Parallel run]

S4 --> S5{Parity met?}

S5 -->|No| S3

S5 -->|Yes| S6[Cutover, rollback ready]

S6 --> S7[Handover and runbook]

K --> D2[D2 Warehouse and AI layer, months 3-13]

D2 --> W1[Ingest Cloudflare logs, GA4 BigQuery, social APIs]

W1 --> W2[Unified data model]

W2 --> W3[AI layer: plain-language query]

W3 --> W4[Automated reporting and anomaly detection]

W4 --> A4[Feeds A4 Looker Studio and A3 GEO reporting]

## Gate rules

- D1.2 starts only after UNICEF's documented go decision (assumption 6).

- D2 sources are limited to Cloudflare logs, GA4 BigQuery exports and agreed social APIs; anything else is a change request (assumption 3).

- Training is capped at 5 hours per quarter (assumption 7).

# 3. Data flow diagram: current and target state

flowchart LR

U[unicef.org and 176 sites] --> WEB[Web GTM container]

CMP[Consent mode / CMP] --> WEB

WEB -->|Phase 1 client-side| GA4[GA4, 180+ properties]

WEB -->|After go: first-party endpoint| SGTM[Server-side GTM on UNICEF Azure]

CMP -->|consent signals| SGTM

SGTM --> GA4

SGTM --> META[Meta CAPI]

SGTM --> ADS[Google Ads links]

SGTM --> PIX[Other pixels]

GA4 --> BQ[(BigQuery GA4 export)]

CF[Cloudflare logs] --> RAW[(Raw zone)]

SOC[Social APIs] --> RAW

BQ --> MODEL[(Unified data model)]

RAW --> MODEL

GSC[Search Console, 176 sites] --> LS[Looker Studio, 150+ offices]

GEO[AI-search visibility] --> LS

MODEL --> AI[AI layer: NL query, anomalies, auto reports]

MODEL --> LS

AI --> ALERT[Alerts and scheduled reports]

AI --> LS

# 4. Run-service workflow (A1-A5, monthly)

flowchart TD

CR[Change request] --> TRI[Triage and impact check]

TRI --> BUILD[Build in GTM workspace]

BUILD --> STAGE[Stage test]

STAGE -->|Fail| BUILD

STAGE -->|Pass| APP[UNICEF approval]

APP --> PUB[Publish and version]

PUB --> MON[Data-quality monitoring in GA4]

MON -->|Issue| CR

NP[New GA4 property request] --> CFG[Configure: Ads link, BigQuery, consent]

CFG --> GOV[Register in governance inventory]

GOV --> MON

SM[Sitemap and GSC error scan] --> ROUTE[Route errors to site owners]

ROUTE --> TRACK[Track to closure]

TRACK --> RPT[Monthly report]

MON --> RPT

RPT --> PM[PM report and budget control]

# 5. Key technical decisions and owners

| Area | Decision | Owner input needed |
| --- | --- | --- |
| Server-side hosting | Azure, funded by UNICEF, with UNICEF DID. Vendor designs and configures. | GTM/GA4 lead |
| Warehouse | BigQuery is the core store. Cloudflare log ingestion and social API pipelines feed one model. | Data engineering lead |
| AI layer | Only UNICEF-approved services; no training on UNICEF data. | Data engineering / AI lead, Legal |
| SEO/GEO tooling | Licences procured by UNICEF unless the commercial proposal says otherwise. | SEO/GEO lead, Finance |
| Access | UNICEF-owned accounts, named vendor users on federated identity. | Information security |

# 6. Reconciling the second assessment with this document

| Topic | Second assessment | This document | Action |
| --- | --- | --- | --- |
| One-off effort | 90-135 days total, AI proof of concept only, full server-side migration excluded | D1.1 30-45, D1.2 60-90, D2 180-300: roughly 270-435 days | The tender lists D1.2 and D2 as priced deliverables, so a proof of concept alone risks scoring poorly on Criteria 2 and 5. Agree the scope boundary with technical owners and state it as an assumption |
| Monthly effort | 30-44 days | About 35-53 days | Reconcile role by role once team availability is known |
| Timeline | 12 weeks to first release, scale-out months 4-6 | Server-side evaluation months 2-5, warehouse months 3-13 | Align with the two-page plan; the longer warehouse timeline is more realistic for a global build |
| Company background | Refers to your .NET architecture and API experience | No information about your company | Confirm accuracy. Relevance is to data integration and the AI layer, not the four-year GA4/GTM/SEO experience gate |
| Minimum technical score | 60/100 | RFPS says 60 of 70; TOR says 60 of 100 | State as an assumption |

The second assessment is consistent with this document on partner model, phasing and security approach.

# 7. Inputs required, by owner

| Owner | Input needed | Used for | Needed by |
| --- | --- | --- | --- |
| Bid lead | Go/no-go; named prime contractor entity; partner decision for D1, D2 and A3 | Whole proposal | Kick-off |
| Bid lead | Annexes C2, C3 and full C bis; UNGM status; business registration | Pricing and eligibility | Immediately |
| Project Manager candidate | CV, availability and dedication percentage; recent comparable engagements | Mandatory gate 2; Criterion 1 | +4 days |
| GTM/GA4 lead | Largest tag and property estate managed; audit and automation tooling; consent mode and Meta CAPI examples; server-side GTM projects, hosting cloud and results | A1, A2, D1.1, D1.2; Criterion 5(a)(b) | +4 days |
| GTM/GA4 lead | Task-level day estimates per activity and per deliverable | Annex C1 bis | +8 days |
| SEO/GEO lead | Largest Search Console estate managed; platforms used; GEO monitoring tools evaluated or deployed; benchmark examples | A3; Criterion 5(c) | +4 days |
| SEO/GEO lead | Day estimates and tool licence assumptions (who pays) | Annex C1 bis | +8 days |
| Data engineering lead | BigQuery and Azure experience; warehouse designs; Cloudflare log ingestion experience; expected data volumes and refresh needs | D2; BigQuery cost model | +4 days |
| Data engineering / AI lead | AI layer design, model hosting choice, data-governance controls, restrictions on third-party model use | D2; Annex B5 data-use rules | +8 days |
| BI lead | Looker Studio template examples, scale of rollout, support model for 150+ offices | A4 | +8 days |
| Training lead | Training samples, delivery formats, languages | A5 | +8 days |
| Information security | Completed section 10 matrix with evidence; certificates; pen-test reports; incident plan; policy on staff use of AI assistants | Mandatory gate 3 | +4 days |
| Legal | Position on GTCs, LTA-S and DSA deviations; partner contract terms; insurance; indemnity | Criterion 4; risk | +10 days |
| Finance | Rate card by role; inflation and FX treatment; partner markup; contingency within capped days; early-payment discount decision | Annexes C1 bis, C2 | +10 days |
| Account/commercial | Case study candidates, reference contacts with written consent, UN or international organisation work | Criteria 1 and 3; Annex B1 | +4 days |

# 8. Stated assumptions (clarification window closed)

1. Access model: UNICEF-owned accounts with named vendor users on federated identity.

2. Azure subscription for server-side GTM is provided and funded by UNICEF; vendor designs and configures.

3. Warehouse sources are limited to Cloudflare logs, GA4 BigQuery exports and agreed social platform APIs; further sources are change requests.

4. The AI layer runs only on UNICEF-approved services and does not train on UNICEF data.

5. SEO/GEO platform licences are procured by UNICEF unless stated otherwise in the commercial proposal.

6. Server-side GTM implementation proceeds only after UNICEF's documented go decision.

7. Training is capped at 5 hours per quarter, as in the TOR.

## Additional proposal assumptions

- One-off scope is D1.1, D1.2 and D2 in full (about 270-435 days); a proof of concept alone is not sufficient. Confirm with technical owners.

- Timeline: server-side evaluation months 2-5; warehouse months 3-13.

- Minimum technical score taken as 60/100 per the TOR (RFPS says 60 of 70).

- Monthly effort reconciled role by role once team availability is known.